## Bug Report
Bug ID | Module | Bug Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reported By
BUG-001 | Login | Password field accepts leading/trailing spaces | Enter password with spaces | Spaces trimmed | Login fails | Medium | High | Open | Saba Sheikh
BUG-002 | Fund Transfer | Zero amount transfer allowed | Transfer 0 | Validation shown | Transfer succeeds | Critical | High | Open | Saba Sheikh
BUG-003 | Beneficiary | Duplicate beneficiary allowed | Add same beneficiary twice | Duplicate prevented | Duplicate added | High | High | Open | Saba Sheikh
BUG-004 | Bill Payment | Bill status not updated | Pay a bill | Paid status | Pending shown | High | Medium | Open | Saba Sheikh
BUG-005 | Registration | Weak password accepted | Register using 12345 | Validation | Registered | Medium | Medium | Open | Saba Sheikh
BUG-006 | Profile | Invalid phone accepted | Update phone with letters | Validation | Saved | Medium | Medium | Open | Saba Sheikh
BUG-007 | Transactions | Wrong date filter results | Filter last 7 days | Correct records | Extra records | Medium | Medium | Open | Saba Sheikh
BUG-008 | Session | Session timeout missing | Idle 20 mins | Auto logout | Session active | High | High | Open | Saba Sheikh
BUG-009 | Dashboard | Balance not refreshed | Transfer funds | Updated balance | Old balance | High | High | Open | Saba Sheikh
BUG-010 | Logout | Back button bypasses logout | Logout then Back | Login page | Dashboard shown | Critical | High | Open | Saba Sheikh